## Arkusz1
TEST SUMMARY REPORT | [5 empty] | TEST SUMMARY
<< Demo OpenCart >> | [5 empty] | TEST SUMMARY
Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Purpose of the tests
12.10.2025 | 13.10.2025 | 12.10.2025 | 13.10.2025 | Post-deployment acceptance testing in production enviroment
Feature/ Section/ Module | Total tests |  | Test Execution Status |  |  | Pass % | Executed Pass % | Total Number of Open Defects | Defects Open |  |  |  | Defects Closed |  |  |  | Defects Count (by status)
| Planned | Executed | Pass | Fail | Pending |  |  |  | Complex | High | Medium | Low | Complex | High | Medium | Low
Registration | 10 | 10 | 5 | 5 | 0 | 50 | 50 | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Assigned : 5 Fixed: 0
Login | 5 | 5 | 4 | 1 | 0 | 80 | 80 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Assigned : 1 Fixed: 0
Links & Navigation | 1 | 1 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assigned : 0 Fixed: 0
Contact Us | 4 | 4 | 3 | 1 | 0 | 75 | 75 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Assigned : 1 Fixed: 0
Product Returns | 17 | 17 | 8 | 9 | 0 | 47 | 47 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | Assigned : 9 Fixed: 0
Cart | 2 | 2 | 1 | 1 | 0 | 50 | 50 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Assigned : 1 Fixed: 0
Search | 2 | 2 | 2 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assigned : 0 Fixed: 0
Wishlist | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Assigned : 1 Fixed: 0
SUMMARY | 42 | 42 | 24 | 18 | 0 | 57 | 57 | 18 | 2 | 4 | 12 | 0 | 0 | 0 | 0 | 0 | Assigned : 1 Fixed: 0
Internal Use Only
Test cases
Test case ID | Test case name | Executed | Test Execution Status |  | BUG ID |  | Status | Number of test cases
[Y/N]
TC01 | User Registration | Y | Pass |  | N/A |  | Pass | 24
TC02 | User Registration | Y | Pass |  | N/A |  | Fail | 18
TC03 | User Registration | Y | Fail |  | B01 |  | Not executed | 0
TC04 | User Registration | Y | Pass |  | N/A |  | Executed | 42
TC05 | User Registration | Y | Fail |  | B02
TC06 | User Registration | Y | Pass |  | N/A
TC07 | User Registration | Y | Fail |  | B03
TC08 | User Registration | Y | Fail |  | B04
TC09 | User Registration | Y | Fail |  | B05
TC10 | User Registration | Y | Pass |  | N/A
TC11 | User Login | Y | Pass |  | N/A
TC12 | User Login | Y | Pass |  | N/A
TC13 | User Login | Y | Pass |  | N/A
TC14 | User Login | Y | Fail |  | B06
TC15 | Logout | Y | Pass |  | N/A
TC16 | Link & Navigation Testing | Y | Pass |  | N/A
TC17 | Contact Us form Testing | Y | Pass |  | N/A
TC18 | Contact Us form Testing | Y | Fail |  | B07
TC19 | Contact Us form Testing | Y | Pass |  | N/A
TC20 | Contact Us form Testing | Y | Pass |  | N/A
TC21 | Product Returns form Testing | Y | Fail |  | B08
TC22 | Product Returns form Testing | Y | Fail |  | B09
TC23 | Product Returns form Testing | Y | Fail |  | B10
TC24 | Product Returns form Testing | Y | Fail |  | B11
TC25 | Product Returns form Testing | Y | Pass |  | N/A
TC26 | Product Returns form Testing | Y | Fail |  | B12
TC27 | Product Returns form Testing | Y | Pass |  | N/A
TC28 | Product Returns form Testing | Y | Pass |  | N/A
TC29 | Product Returns form Testing | Y | Fail |  | B13
TC30 | Product Returns form Testing | Y | Pass |  | N/A
TC31 | Product Returns form Testing | Y | Pass |  | N/A
TC32 | Product Returns form Testing | Y | Fail |  | B14
TC33 | Product Returns form Testing | Y | Fail |  | B15
TC34 | Product Returns form Testing | Y | Pass |  | N/A
TC35 | Product Returns form Testing | Y | Fail |  | B16
TC36 | Product Returns form Testing | Y | Pass |  | N/A
TC37 | Product Returns form Testing | Y | Pass |  | N/A
TC38 | Adding a product to the cart | Y | Pass |  | N/A
TC39 | Adding a product to the cart | Y | Fail |  | B17
TC40 | Product Search | Y | Pass |  | N/A
TC41 | Product Search | Y | Pass |  | N/A
TC42 | Adding to wishlist | Y | Fail |  | B18
Reported bugs
Bug ID | Bug title | Priority | Severity |  |  |  | Priority | Nuber of bugs
B01 | User Registration – Verify First Name field validation for special characters | High | High |  |  |  | high | 7
B02 | User Registration – Verify Last Name field validation for special characters | High | High |  |  |  | low | 1
B03 | User Registration – Verify Password field length | High | Complex |  |  |  | medium | 10
B04 | User Registration – Verify acceptable password field content | High | Complex
B05 | User Registration Form Submission- Acceptance of the correct form | Medium | Medium
B06 | Password recovery – Login | High | High
B07 | Contact Us Form Testing - Validate First Name field | Medium | Medium
B08 | Product Returns Form Testing – Verify First Name field validation | Medium | Medium
B09 | Product Returns Form Testing – Verify First Name field validation for special characters | Medium | Medium
B10 | Product Returns Form Testing – Verify Last Name field validation | Medium | Medium
B11 | Product Returns Form Testing – Verify Last Name field validationfor for special characters | Medium | Medium
B12 | Product Returns form – Verify Telephone field validation | Medium | Medium
B13 | Product Returns form – Verify Order Date field (future date validation) | Low | Low |  |  |  | Severity | Number of bugs
B14 | Product Returns form – Verify Product Name field validation | Medium | Medium
B15 | Product Returns form – Verify Product Code field validation | Medium | Medium |  |  |  | low | 1
B16 | Product Returns form – Verify “Quantity” field validation | High | High |  |  |  | medium | 10
B17 | Verify that not available product cannot be added to the shopping cart | High | High |  |  |  | high | 5
B18 | Wishlist - verifying product adding to wishlist | Medium | Medium |  |  |  | complex | 2